## Sheet1
引用编号 | 标题 | 故事 | 初始时间（h） | 优先级 | 估算时间（h） | 进度
1 | QQ登录 | 作为一个普通用户，我希望能够通过QQ登录，以便于更快捷的登录系统，而省去注册环节。 | 2 | 100 | 2 | 未完成（部分未写）
2 | 手机登录 | 作为一个普通用户，我希望能够通过手机验证码登录，以便能够更加安全 | 2 | 90 | 2 | 已完成
3 | 基本垃圾分类 | 作为一个普通用户，我希望能够了解一下最基本的垃圾分类知识 | 2 | 90 | 2 | 已完成
4 | 订单跟踪 | 作为一个普通用户，我希望能够跟踪工作人员的位置，以便了解订单的详情状态 | 1 | 95 | 1 | 未完成（订单创建）
5 | 快捷搜索 | 作为一个普通用户，我希望能够使用快捷搜索，可以通过提示，以便节省时间 | 4 | 90 | 4 | 已完成
6 | 拍照识别 | 作为一个普通用户，我希望能够使用拍照识别，能够方便的解决不知道垃圾名称的问题 | 8 | 80 | 8 | 已完成
7 | 社区发布动态 | 作为一个家庭用户，我希望能在社区发布自己的动态，能和大家一起交流 | 4 | 70 | 4 | 已完成
8 | 聊天 | 作为一个普通用户，我希望能和工作人员进行沟通，以便解决某些特殊问题 | 2 | 90 | 2 | 已完成
9 | 历史订单 | 作为一个普通用户，我希望能够查看自己的历史订单，以便能够了解该APP的使用情况与频率。 | 2 | 100 | 2 | 已完成
10 | 答题挑战 | 作为一个普通用户，我希望能够进行答题挑战，来进行对自己当前垃圾分类知识的测试 | 2 | 100 | 2 | 已完成
Note on A1: Luc Segers: This is the highest reference ID number used so far.
Note on A2: Luc Segers: This reference ID should be unique. This number is used throughout the whole worksheet so be aware.
Note on C2: Luc Segers: This is the story (Feature, Epic, User). Depending on in which phase you are in (Présales, Scope, …) the detail could be higher. Normally you could describe a user story as follow: As a <Role> I can do <this> and the result is <that> ... Offcourse this is not always possible, so you should be creative. A story should conduct to the following rules: I = Independent N = Negotiable V = Valuable to customer E = Estimatable S = Small T = Testable
Note on D2: Luc Segers: This column is calculated: Ideal Hours * Adjustment Factor
Note on E2: Luc Segers: M = Must Have S = Should Have C = Could Have W = Won't have this time